# National Capital Heavy Construction Association (NCHCA) / City of Ottawa

# NOTES

Date:  Friday, May 19, 2023

Time:  10:00 am to 10:45 am

Place:  Microsoft Teams

PRESENT

Bruce Kenny, Luc Marineau, Joanne Graham, Danny Palermo, Sandra Majkic, Robert Leach, Matt Knight, Erin O’Neill, Sajjad Haque, Chris Malloy, Renjit Varghese, Rebecca Belrango

Kathy Sutherland, Madison Johnson, Darrin Alberty, Nick Gianetto, Geoff Falls, Yannick Lamontagne, Ivan Levac, Brian Lane, Dale Downey, Edson Donnelly, Debbie Mohr Caldwell

- Review Notes of Previous Meeting

Pre-payment for materials and storage - The City has been getting more requests for pre-payment of materials.  Space and security at City facilities is limited.  In order to ensure that the materials are available when needed, the City will have conditions for pre-payment.  The Industry noted that Contractors have insurance for material stored on site.  They also suggested that January/February is a good time to work on a framework for this issue.  Supply noted that pre-payment is an exception to City Policy and will provide some additional clarification to the industry on pre-payment of materials.  More discussion is needed. The City will work with the Industry; this may require changes to contract specifications.  Bruce to discuss with NCHCA reps at their monthly meeting and loop in Supply if necessary.

Follow-up – The City will try to shore up for the next Spec Update.

Pre-populated unit rates - The Industry provided examples of rates that are out of date.  The City suggested that the Industry send over a list of the rates they would like increases on to the spec committee.  A breakdown of co-ordination, third party costs, etc will be provided for Paid Duty Officer item. NCHCA to send information.  City is open to change. NCHCA will provide information to the City.  City to review along with the fuel price index.  It was clarified that VPM scores are frozen the day prior to postings.

Follow-up – The City is working on having something to share with the Industry next week.  The fuel price index will be adjusted soon.

Paid Duty Officers - Continues to be an issue and the City is looking at options to address it.  After the Educational Series, and before construction season starts, a meeting will be set up with NCHCA/City/Locates/OPS representatives to discuss.  This will be a topic at the Educational Series. Sgt. Nethercott gave a presentation at the Educational Series.  He noted that OPS prioritizes the City’s Infrastructure work. The City has set up a meeting with the OPS and NCHCA to discuss. Meeting with OPS has taken place.  They will continue to work with us on issues.  There is a new liaison at the OPS, Sgt. Brownrigg.

Follow-up – the City anticipates that this will be an issue again this year due to the amount of work taking place.  The Industry asked if the City would consider paying OPS directly.  The City believes the most appropriate and consistent approach is to have the CA/site coordinate and pay for this activity.

Holdback release – MTO does a partial annual release.  Would the City consider doing the same?  The City is willing to consider this on large, multi-year contracts but ideally this would be built into the original contract documents. DCM has been working with legal. Need to build into original contracts.  IS will work with Legal and Supply to build into future, large scale projects.  This will not apply to existing contracts.

Follow-up – the City will do a pilot this year on a large scale, multi-year project.

New Enbridge Locate Fees - Enbridge recently announced new locates fees of $200 per locate.  Bruce touched base with other municipalities.  Everyone was caught off guard by these new fees.  The Industry noted that they have been working with stakeholders including the City to mitigate non-compliance by the utilities. Industry feels these fees are working in the opposite direction.  One core and immediate issue is the lack of notice, as these costs would not have been accounted for in submitted bid prices for upcoming work. The City is concerned with cost escalations and costs implications as the issues will flow down to the project owners. The City is working on the issues but the Industry may need to escalate the issue directly to the Ministry and ON1Call (the City is willing to be in the room with NCHCA), rather than discussing directly with Enbridge.  The City is open to working with the NCHCA and meeting to determine the industry lobby strategy.   Enbridge has withdrawn the locate fees for now but has an application before the Energy Board regarding the fees. Industry to send Bruce metrics of anticipated costs if all utilities started charging $200.  Bruce to bring the cost implications on capital projects to senior management.

Follow-up – The City is working with the Industry on locate issues in the Province.

City’s Annual Spec Review – It was suggested that the spec review changes be issued in the Fall instead of the Spring.  The City noted that in order to do this they would need to have the spec review committee start in the summer months.  The City will look at the possibility of moving up the release date by a month.

Follow-up – ACEC AGM will put forward names to Sandra to participate.

- 2022 overlay program

With shutdowns and start ups the strike last year had a significant impact on Contractors.  The Industry feels that the City’s estimate of lost time at 20 days is short of the actual time lost and are concerned about being charged liquidated damages.  Also of concern is the City wanting to keep last years prices.  The Contractors wanted to make up some time before half loads were lifted but were met with punitive results.  The City and Industry will meet to discuss this issue further.

Action – Cheryl to set up meeting

- Roundtable

Missing information in tenders – Industry is concerned with recent contracts missing information on rates.  The City committed to implementing quality control on upcoming work tendered.

Quantity Sheets – more information is needed on quantity sheets not just lump sums.  A breakdown would be helpful for more accurate bids.  The City is reviewing quantity sheets next week.  A detailed breakdown will make things more transparent.

Leeway for permitting tender extensions – The City will extend tender closings when possible.  Extensions are scrutinized due to workflow and timelines.  There needs to be a balance.

Excess Soils – The industry would like the information of where the soil is going highlighted in tender documents.  They recommend that the spec be reviewed with a contract lens.  The City reminded the industry to read the spec carefully as there may be slight differences from one tender to another.

### NEXT MEETING Friday, June 16, 2023 8:00 – 10:00 pm Microsoft Teams